## Sheet1
CSL Project - Group 4
Project Name: Development of software Resources to Compliment Student Mental Health Services
Project Start Date: 01/23/2024
Project End Date: 03/27/2024
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
 | time axis 2024-01-22 to 2024-03-27
TASK | PROJECT LEAD | START DATE | END DATE | PROGRESS | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Initial planning stage
Project choice | Group 4 | 2024-01-23 | 2024-01-23 | 100% | 1 | bar: 2024-01-23
Initial project proposal | Group 4 | 2024-01-26 | 2024-01-26 | 100% | 1
letter to the beneficiary V1 | Group 4 | 2024-01-26 | 2024-01-26 | 100% | 1
Project proposal V2 | Group 4 | 2024-01-26 | 2024-01-26 | 100% | 1
Project proposal V3 | Group 4 | 2024-02-02 | 2024-02-02 | 100% | 1
First Formal Site Visit | Group 4 | 2024-03-12 | 2024-03-12 | 100% | 1 | bar: 2024-03-12
Final Project proposal | Group leader | 2024-02-09 | 2024-02-09 | 100% | 1
Application Devlopment
Coding Development | Development team | 2024-01-26 | 2024-03-13 | 100% | 47 | bar: 2024-01-26 to 2024-03-13
Introducing code requirements | Development team | 2024-01-26 | 2024-03-13 | 100% | 47 | bar: 2024-01-26 to 2024-03-13
Integrating forms | Development team | 2024-01-26 | 2024-03-13 | 100% | 47 | bar: 2024-01-26 to 2024-03-13
Testing | Development team | 2024-03-13 | 2024-03-20 | 100% | 7 | bar: 2024-03-13 to 2024-03-20
Documentation
SyRS Document | Documentation team | 2024-02-28 | 2024-03-26 | 100% | 21 | bar: 2024-02-28 to 2024-03-26
SDD Document | Documentation team | 2024-03-02 | 2024-03-26 | 100% | 18 | bar: 2024-03-02 to 2024-03-26
First Formal Site Visit report | Documentation team | 2024-03-12 | 2024-03-26 | 100% | 14 | bar: 2024-03-12 to 2024-03-26
STP Document | Documentation team | 2024-03-10 | 2024-03-26 | 100% | 10 | bar: 2024-03-10 to 2024-03-26
Risk Assessment | Documentation team | 2024-03-12 | 2024-03-26 | 100% | 8 | bar: 2024-03-12 to 2024-03-26
Final Project Breakdown
Approved forms | Group leader | 2024-02-28 | 2024-02-28 | 100% | 1 | bar: 2024-02-28
Final Report Video | Group 4 | 2024-02-29 | 2024-03-26 | 100% | 26 | bar: 2024-02-29 to 2024-03-26
Final Report | Group 4 | 2024-03-15 | 2024-03-27 | 100% | 12 | bar: 2024-03-15 to 2024-03-27
Complete Presentation | Group 4 | 2024-03-17 | 2024-03-26 | 100% | 8 | bar: 2024-03-17 to 2024-03-26
Handover Ceremony | Group 4 | 2024-03-20 | 2024-03-27 | 100% | 7 | bar: 2024-03-20 to 2024-03-27

## ©
© TemplateLab.com